## Slide 1: FFRD Validation Basins Cross-Basin Meeting
April 17th, 2026

## Slide 2: Agenda
Introduction - FEMA
Basin Status
Technical Discussions
Basin SO3.2 Scope

## Slide 3: Status Update
FFRD Task | End of March (SO3.1 Progress)
Scoping & Data Preparation | Compiled relevant available reference/input data Identified key data providers and datasets Geospatial Completed 4-ft and 100-ft DEM base terrain Dam/Levee Draft Dam and Levee Scoping Tables
Meteorology | Collected Base Atmospheric Data Storm Catalog (SLAM-SIM v1) Storm Typing, Normalization Grid, Seasonality Analysis
Hydrology | Uncalibrated HMS Model Developed Gage Data Prioritized Calibration Events Identified
Hydraulics | RAS Model Unit Delineation
Documentation & Feedback | Draft Project Workplans, Data Manifest, Report
FEMA Standard Operations Option Period 1 ended March 29th
Interim Deliverables posted to FEMA AWS bucket
Option Period 2 Near-Term Goals
Maintain progress on Validation Basins within limits of Standard Operations funding requirements
Prioritize work that minimizes risk of rework or sequencing conflicts with SOP
  Bonus if not dependent on Data Provider Outreach
Focus on targeted, small-team tasks that advance readiness without full production-scale resources

## Slide 4: Identified Tasks for Standard Operations Option Period 2
 | Prioritized | Possible | Dependent on Outreach | Dependent on USACE IRWA
Scoping and Data Preparation | Data Provider Outreach | Collect all FEMA Models Urban Stormwater Scoping | Refine Previous Deliverables | 
Geospatial | Specify EDH Requirements | Begin EDH Development Standardize Metadata/Attributes | Collect and Incorporate Bathymetric Data | 
Meteorology | Transposition Domain Evaluation Refine Meteorology Deliverables |  |  | 
Hydrology | Refine Parameters Continue Flood Mechanism Analysis (Mixed Populations) | Continue Calibration Event(s) Selection/Collection | Refine HMS Model Add Reservoirs | 
Hydraulics |  | Pilot 1 RAS Model Per Basin |  | 
Dam/Levee |  |  | Finalize Dam Scoping Table | SRP Source Data Collection
Review and Reporting | Maintain SOP Feedback |  | Finalize Report and BE-PWP Internal Review | Early Basin-Advisor Review

## Slide 5: Technical Discussions
04-17-2026

## Slide 6: SLAM-SIM vs. SLAM-SIG Domain Selection
Current Meteorology work to date based on SLAM-SIM version 1 (24/72hr) overlap
  Received February 13th
Since then, a new version of SLAM-SIM and SLAM-SIG domains have been posted
  SLAM-SIG domains contain both 72hr and 24hr versions, with varying GSLs
PTS to evaluate various domains in consistent manner to determine consistent domain usage
  Utilize PRISM comparison metrics from South Platte Transposition Domain Investigation (Mar 2026)

## Slide 7: SLAM SIM version differences
SLAM-SIM
(2/13)
SLAM-SIM
(3/31)
Upper Tennessee SLAM-SIM Versions

## Slide 8
SLAM-SIG
SLAM-SIM
Error to domain size comparison.
HUC4: 0501, Allegheny River Basin (72-hr)
Reference: Slides from Dan Wright – UW/UNC Team

## Slide 9
SLAM-SIG
SLAM-SIM
Error to domain size comparison.
HUC4: 0601, Upper Tennessee River Basin (72-hr)
Reference: Slides from Dan Wright – UW/UNC Team

## Slide 10
HUC4: 1019, South Platte River Basin (72-hr)
SLAM-SIG
SLAM-SIM
Error to domain size comparison.
Reference: Slides from Dan Wright – UW/UNC Team

## Slide 11: Implementation of Urban Stormwater Investigation
Confirm that the decision was to implement Urban Stormwater investigation findings into Validation Basins
PTS to provide discrete criteria and tools/methods to implement for consistency amongst validation basins
  Surface Characterization & Key Collection Point Filtering
  Hydraulic Routing Considerations
How might this alter some activities in the Scoping and Data Preparation phase?

## Slide 12: Implementation of Urban Stormwater Investigation
Create a Job Aid & Process/Tool
  Within Each Urban Area
  Perform Surface Characterization Process/Tool
    Key Filters
      Contributing Area (Refinement Extent)
      Maximum Potential Consequences (NSI)
    Outcome
      Highlight Key Refinement Areas
      Derive Initial HEC-RAS Breaklines
  Update Scoping & Data Preparation Documentation
  Use Collected Data in Hydraulics

## Slide 13: RAS 2025 vs RAS 6 Mesh for Validation Basins
Open discussion on opinions of using RAS 2025 to develop meshes for Validation Basins.
Pros
  Better mesh capabilities and alignment
  Potentially more efficient run times for level of detail
Cons
  Still in Beta version
  Could lead to some inefficiency and troubleshooting
    Develop RAS 2025 mesh > export to RAS 6 > all subsequent edits need to go through RAS 2025 (2 versions of each model)
  Deviation from SOP

## Slide 14: EDH and Terrain Modification Specifications
Feedback: SOP could be further specified in this area
SOP(JA2)
  “All identified streams with a drainage area of greater than 0.25 square miles should be included in the EDH delivery.”
  “Efforts to align with USGS 3DHP program priorities for data development should be made.”
For basins this size, this could be a large effort to…
  manually refine of hydro connected terrain modifications to generate accurate flowlines
  Develop USGS 3DHP spec: which includes additional attribution, 1m Horizontal accuracy, vertical components, QC
Consider: level of effort, accuracy/resolution, and intended uses
  Clarify uses for EDH in FFRD
    Mesh Refinement, Terrain Modifications, Bathymetry (Primary Streams), Mapping Quality, others?

## Slide 15: EDH and Terrain Modification Specifications
Questions for USACE:
Clarify
  Statement about aligning with USGS 3DHP Program Priorities
  How 0.25 square mile drainage area limit was determined? Was this used in pilot projects?
Speak to Lessons Learned from Pilot Projects
  How was EDH developed in pilot areas?
  Any considerations for accuracy requirements? Were there any instances were errors in EDH impacted downstream processes?
Considerations:
Align EDH specific requirements to Primary/Secondary stream levels of detail
  Add "Channel Present" requirements in addition to drainage area.
  Variable Drainage Area based on Geography
Was there or should there be consideration given to existing level of detail/refinement expectations?
Does RAS2025 conceptual mesh potentially alter uses of EDH?