Validation Basin Bi-Weekly Coordination Call, 2/6/26

Introduction:

- Meeting opened as the first in a planned series of technical discussions for FEMA’s Validation Basin effort.

- Purpose emphasized:

  - Create a technical forum for discussion and shared learning

  - Validate the FFRD SOP v1 when implemented by PTS teams

  - Capture lessons learned to inform SOP v2

- Validation basins framed as a testing and learning environment, not a production exercise.

- SOP v1 released in December.

- Validation effort intended to test:

  - Whether the SOP is sufficiently prescriptive

  - How transferable the workflow is outside USACE

  - Where flexibility may be necessary

- Goal is eventual national consistency with reduced dependence on USACE oversight.

- Emphasis on documenting challenges, gaps, and deviations.

Validation Basins Overview

- Three basins introduced, selected for diversity in hydrology, geography, and infrastructure:

  - Upper Tennessee Basin (Compass)

  - Allegheny Basin (ARC)

  - South Platte Basin (STARR II)

- Differences across basins noted as intentional and valuable for testing SOP robustness.

FFRD Workflow & Current Phase

- Overview of the five-phase FFRD workflow:

  - Scoping & Data Preparation

  - Calibration

  - Conformance

  - Production (Monte Carlo)

  - Outputs

- Validation basins currently in Phase 1.

- TOG reviews will occur between phases.

- Phase 1 activities include data collection, storm catalogs, HMS setup, and documentation.

- Funded through March 31.

- Focus remains on scoping and foundational setup.

- Phase 2 anticipated to begin around April, pending funding.

- Teams cautioned to avoid overextending scope beyond validation objectives.

Roles, Coordination, and Expectations

- FEMA HQ identified as program lead.

- FEMA Regions discussed as optional participants due to bandwidth constraints.

- Regional roles include:

  - Data provider outreach

  - Ensuring defensibility and usability

  - Flagging regional sensitivities

- USACE role emphasized as:

  - SOP authors

  - Technical advisors (not implementers)

- PTS teams responsible for implementation and documenting lessons learned.

- Discussion of outreach to local, regional, and federal data providers.

- Priority data includes:

  - Existing H&H models

  - Gauge and high water mark data

  - Flood imagery

  - Dam and levee information

- Acknowledged that dam data availability varies significantly, but outreach is encouraged where feasible.

Upper Tennessee Basin (Compass)

- Basin characteristics discussed, including:

  - TVA-controlled reservoirs

  - Mountainous and karst terrain

  - Hurricane Helene as a recent calibration event

- Progress reported:

  - Public data compilation

  - Terrain generation

  - Initial dam and levee scoping

  - Identification of calibration events

- Key next steps include TVA coordination and storm catalog development.

Allegheny Basin (ARC)

- Basin complexity highlighted:

  - High number of dams and levees

  - Urban challenges in Pittsburgh

  - Snowmelt and ice considerations

- Progress updates:

  - Levee refinement review underway

  - Scoping tables developed

  - Initial storm transposition domains identified

- Emphasis placed on early coordination to avoid schedule delays.

South Platte Basin (STARR II)

- Basin characteristics discussed:

  - Snowmelt-dominated hydrology

  - Extensive dam and diversion systems

  - Irrigation and sediment considerations

- Progress updates:

  - Use of machine-readable data catalogs

  - Compilation of terrain, gauge, dam, and levee data

  - Initial event ranking and storm driver classification

Additional technical discussion:

Levee Terrain Resolution

- Question raised about terrain resolution differences:

  - NLD SOP uses 1m terrain

  - FFRD SOP uses 4-ft terrain

- Discussion focused on whether levee refinements need to be redone.

- Preliminary consensus:

  - Existing refined levees may be reused after comparison

  - New refinements should continue using 1m terrain

- No major discrepancies observed to date.

Storm Typing in South Platte

- South Platte team raised concern that SOP storm typing (tropical vs. non-tropical) may be insufficient.

- Discussion acknowledged:

  - SOP simplification driven largely by coastal basin needs

  - Importance of seasonality and realistic antecedent conditions

- Tension noted between:

  - Strict SOP adherence

  - Basin-specific realism

  - No final decision reached.

- South Platte team asked to propose a limited, well-documented path forward.

End Remarks:

- Validation basins reaffirmed as a learning exercise.

- SOP deviations are acceptable if:

  - Clearly documented

  - Justified and scoped

- Emphasis on transparency, communication, and avoiding scope creep.

- Future meetings will continue technical discussions and track lessons learned.